Republika e Kosovës

Republika Kosova - Republic of Kosovo

Qeveria – Vlada – Government

STATE ARCHIVES STRATEGY 2025-2032

January 2025

CONTENTS

- EXECUTIVE SUMMARY

- LIST OF ABBREVIATIONS

- METHODOLOGY

- BACKGROUND;

- VISION AND OBJECTIVES OF THE STRATEGY

- IMPLEMENTATION, MONITORING AND REPORTING ARRANGEMENTS

- BUDGETARY IMPACT AND IMPLEMENTATION OF THE STRATEGY

- ACTION PLAN 2025 - 2030

- EXECUTIVE SUMMARY

The Kosovo State Archives Strategy (SAS) 2025-2032 is the primary document outlining the objectives, plans, concrete actions and measures of institutions and other stakeholders within a strategic framework aimed at achieving these objectives. The Strategy addresses challenges and priorities that enable the preservation, administration, presentation and utilization of archival material as a sign of society’s and the state’s care and respect for collective memory.

The Kosovo State Archives Strategy (SAS) 20252032, the first of its kind in the Republic of Kosovo, emerges as a response by public policy-making and implementation authorities in the area of archives. It reflects the current assessment of the conditions and general circumstances regarding the preservation of archival material at various levels in Kosovo, ranging from storage conditions in competent archives, including archives under the administration of the Kosovo State Archives Agency (KSAA), archives of record creators/holders, special archives, private archives, etc. The Strategy also identifies and evaluates structural and objective problems, analyzing their causes and consequences in the current archival landscape in the Republic of Kosovo. The aim is to define objectives, measures and coordinated actions that facilitate the establishment of a sustainable, modern, secure and efficient system for the preservation, protection, processing, regulation, administration and utilization of archival material in accordance with international archival standards.

Based on the current situation assessment, the vision of the Strategy is to develop a competent, professional archival service capable of ensuring the sustainable preservation of archival material in the Republic of Kosovo.

The Strategy consists of five (5) strategic objectives, namely: 1. Creating conditions for the acceptance/delivery and preservation of matured archival material in the competent archive, in accordance with international conditions and standards; 2. Strengthening the processes of processing and regulation of archival material; 3. Digitalizing archival material and digital archival services; 4. Enhancing the research, promotion, cooperation, publishing and scientific research component through archives; 5. Consolidating the implementation capacities of the Kosovo State Archives Agency;

These five (5) strategic objectives are further broken down into specific objectives, with medium- and long-term indicators set for their achievement. The expected outcomes are further clarified and resource allocation is oriented towards eliminating the causes and consequences of identified problems.

Given that the legislation of the Republic of Kosovo regarding the creation, care, preservation, protection, processing, regulation, administration and utilization of archival material establishes correlative rights and obligations at various levels of governance and functionality, both for public authorities and non-public entities, it has been deemed essential to develop an integrated strategic framework with inter-institutional obligations. This approach aims to fully address challenges and achieve the objectives of transforming and modernizing archives and archival science in the Republic of Kosovo.

The Strategy includes a three-year (3) Action Plan, which outlines concrete, coherent and comprehensive/inter-institutional activities for achieving these objectives.

In conclusion, the implementation of this Strategy is expected to have a certain budgetary impact and will significantly increase the activities of institutions responsible for legal obligations. Additionally, the Action Plan of this Strategy will particularly impact the Kosovo State Archives Agency, as the institution mandated by Law No. 08/L-111 on Archives as the sole executive institution of the state administration responsible for organizing, directing and overseeing archival activities in the country.

The Strategy will also have monitoring structures and periodic evaluations to assess the achievement of results and the fulfillment of the defined objectives.

LIST OF ABBREVIATIONS

GRK – Government of the Republic of Kosovo

MCYS – Ministry of Culture, Youth and Sports

KSAA – Kosovo State Archives Agency

OPM – Office of the Prime Minister

GCS – Government Coordination Secretariat

OSP – Office for Strategic Planning

MIA – Ministry of Internal Affairs

MFLT – Ministry of Finance, Labour and Transfers

KIPA – Kosovo Institute for Public Administration

CGMISAS – Coordination Group for Monitoring the Implementation of the State Archives Strategy

- INTRODUCTION

Archival material is created because of organized social, state and public activity and as an expression of the socio-cultural, political or other engagement of individuals, groups and organizations of public interest for the state and society. Accordingly, the creation, receipt, preservation, protection, organization, processing and utilization of archival material is a fundamental duty of society and the state, manifested through the legal and structural regulation of the public archival service.

The Republic of Kosovo has an organized archival service consisting of competent archives, as defined by Law No. 08/L-111 on Archives, while in previous periods, the area of archives traces its beginnings to 1951, when it first began operating in an organized manner through the relevant archival institution.

Beyond the establishment and transmission of significant administrative and professional archival experience, as well as the measures implemented thus far towards effective management, archives in the Republic of Kosovo still face structural challenges. These challenges stem from a broader spectrum of regulatory and enforcement measures required to address them, as well as from the responsibilities of both levels of government organization and functioning in the Republic of Kosovo. Consequently, the lack of a long-term, comprehensive and cohesive inter-institutional strategic framework is considered one of the main sources of the identified challenges in the field of archives. Therefore, the development of a long-term strategic planning system, with a broad spectrum of inter-institutional activation and coordinated measures derived from the responsibilities of stakeholders involved in archive management, is deemed crucial.

The Ministry of Culture, Youth and Sports (MCYS), which is responsible for drafting and developing policies in the area of archives, has assessed that public policy in this area, beyond the strategic orientations outlined in the National Development Strategy (NDS), is not sufficiently consolidated in the form of objectives and planned actions that are integrated and developed within the principles of strategic planning. As a result, this has led to a reduction in opportunities, space and resources available for advancing and developing a capable and modern archival service to protect, preserve, organize and ensure the use of archival material.

The State Archives Strategy (SAS) aligns with the Government Program of the Republic of Kosovo 2021–2025 and, more specifically, with Section 2.16 [culture, youth, and sports], which prioritizes the advancement of physical and legal infrastructure and the creation of working conditions, among other aspects, also for KSAA. Based on the legal mandate of KSAA and other competent archives, it is also recognized that the use of archival material is made available for not only research, investigative and scientific activities but also for social and legal needs of citizens in realizing and protecting their individual rights recognized by the Constitution and the law. Both of these aspects fall under the fundamental rights of citizens to free and unhindered access to information, as protected and guaranteed by Chapter II of the Constitution of the Republic of Kosovo. In this way, the Strategy supports the priorities of the Government of the Republic of Kosovo, particularly the Government Program – on the rule of law, good governance, public administration modernization, education, science etc..

As the main policy framework document in the area of archives, the Strategy is also in line with the National Development Strategy (NDS), specifically with Pillar III – Security and the Rule of Law and Pillar IV– Good Governance.

Apart from the introductory section and the methodology of its drafting, which constitute the first two chapters, Chapter III presents the Background of the Strategy, highlighting recent developments and existing challenges in the area of archives in Kosovo. Chapter IV – Vision and Objectives of the Strategy defines the vision, strategic objectives (a total of 5), and specific goals (a total of 21) that the Government of Kosovo aims to achieve by 2032. Furthermore, Chapter V outlines the implementation, monitoring and reporting arrangements with the goal of establishing an efficient implementation system and adequate monitoring mechanisms, where the primary role will be played by the Kosovo State Archives Agency (KSAA) and the inter-institutional coordination team that will be established for this purpose. Chapter VI presents the cost of implementing the Strategy, specifically the planned actions within the Strategy Action Plan, which is an integral part of it.

- METHODOLOGY

The Ministry of Culture, Youth and Sports (MCYS) and the Kosovo State Archives Agency (KSAA), while developing plans for 2025, have assessed a fundamental lack of integrated information regarding investment needs and other support measures in the field of archives. Consequently, they have proposed in KSAA’s Work Plan the drafting and adoption of the State Archives Strategy (KSA) within 2025.

In the first half of 2025, the Ministry of Culture, Youth and Sports, in accordance with the applicable normative acts regulating the procedures for drafting strategic documents, established a Working Group consisting of representatives from KSAA, MCYS, the Legal Office of the Office of the Prime Minister(LO/OPM), the Office for Strategic Planning within the Office of the Prime Minister (OSP/OPM), the Ministry of Internal Affairs (MIA), and external experts, among others.

Following initial meetings and agreement on the Work Plan and respective tasks for the Working Group, questionnaires and forms were developed to collect specific information to ensure a comprehensive and thorough problem analysis. This analysis aimed to document and quantify the consequences and root causes characterizing archival activities in Kosovo. The Working Group took a careful approach in structuring the framework for data collection, ensuring both the breadth and depth of the gathered information, primarily focusing on:

- Factual and documented information regarding archival units within the Kosovo State Archives Agency;

- Factual and documented information concerning the archives of record creators and record holders;

Factual information derived from inspection and control reports conducted by KSAA over the years as part of its activities.

An essential source of information, cross-referenced with other collected or updated data, was the 2022 KSAA Report on visits to record creators. Through field visits conducted by professional KSAA staff, this report aimed to determine the exact quantity, condition, storage environment, and fundamental details of archival material held by record creators. This project is considered the most comprehensive and it therefore contains the most consolidated information from all other sources. As such, it has been utilized to assess, document, and target the harmful consequences and their causes during the drafting of this Strategy.

Another key source of information for the problem analysis in the area was the distribution of relevant questionnaires and forms to record creators, along with a specific form for KSAA’s archival units.

The Working Group primarily carried out its tasks through electronic data exchanges, in addition to several workshops held to draft sections and chapters of the Strategy, which were continuously consulted with the Working Group.

The formulation of objectives was based on an analysis of the gathered information concerning the addressed problem, followed by a SWOT analysis. This analysis was instrumental in highlighting the external and internal environment of the identified issue.

- BACKGROUND

General assessments:

The creation, receipt, preservation, protection, organization, processing and utilization of archival material involve a large number of institutions, officials, organizations, individuals,\ and entire administrative, technical, technological and infrastructural systems. As a result, the preservation, administration and overall management of archives require coordinated institutional approaches, as well as diverse measures and approaches from public authorities and other stakeholders participating in this interconnected cycle of authorities and official entities.

In Kosovo, as elsewhere, coordination, cooperation and collaboration among public institutions, not only among archival units, are essential for achieving the desired outcomes in this area.

Within the chain of responsible mechanisms for the creation, preservation, protection, organization, processing and utilization of archival material, everything begins with the institutions that have created or continue to create archival material through their activities. As a general rule, these institutions are obligated to (i) Preserve and manage this material for 30 years; (ii) Classify, process and organize it according to professional criteria; (iii) Store and protect it under acceptable conditions defined by international standards; and (iiii) Upon expiration of the legally defined period, transfer the archival material in an orderly manner to the competent archive for permanent preservation.

| No. | OBLIGATIONS OF RECORD CREATORS |
| --- | --- |
| 1. | Every record creator is required to have a responsible archival unit, known as the archive of the record creator |
| 2. | The record creator is obliged to maintain the material they possess and create in accordance with the criteria set forth in the Law and other legal acts until it is transferred to the competent archive for permanent preservation; |
| 3. | Record creators/holders of archival material are required to notify the Agency about the quantity, type,and condition of all archival material older than thirty (30) years. |
| 4. | Record creators/holders of archival material older than thirty (30) years are responsible for initiating the procedures for transferring the material to the Agency in accordance with the procedures defined in Law No. 08/L-111 on Archives, the Regulation and other applicable normative acts. |
| 5. | Creators and holders of archival material, specifically legal and natural persons possessing archival material, are required, after fulfilling the legal obligation for the selection of archival material with permanent value, to deliver it to the Agency in an organized, regulated and registered manner in its original form as a whole, or to comply with legal obligations as specified in Article 13 of the Law. |
| 6. | A record creator/holder managing selected/organized archival material up to 100 linear meters is required to have at least one (1) qualified, trained and certified archivist employed in the document management unit – the archive of the record creator/holder. |
| 7. | A record creator/holder managing selected/organized archival material exceeding 100 but under 1000 linear meters is required to establish and organize a responsible unit within their structure with at least three (3) qualified, trained, and certified archivists in the document management unit – the archive of the record creator/holder. |
| 8. | A record creator/holder managing selected/organized archival material exceeding 1000 linear meters is required to establish and organize a responsible unit within their structure with at least six (6) qualified, trained and certified archivists in the document management unit – the archive of the record creator/holder. |
| 9. | Institutions or entities that fall within the scope of Law No. 08/L-111 on Archives (hereinafter referred to as the Law) are required to provide detailed information on the material they manage within the operation of the public archival register as defined in Article 9 of the Law. |
| 10. | Every record creator/holder is required to draft the List of Unique Classification Marks and Document Retention Periods, which is approved after obtaining consent from the Kosovo State Archives Agency. |
| 11. | The record creator/holder is required to destroy invalid material at least once every five (5) years. |
| 12. | The record creator/holder is required to notify the Agency’s Inspectorate before initiating the selection/destruction process, providing details on the time, place, type, quantity, and other specifics of the selection/destruction. |
| 13. | The record creator/holder is required to draft a register of invalid material proposed for destruction. |

The cooperation and coordination of activities in managing archival material between the archives of record creators and the competent archives responsible for permanent preservation are generally minimal and unstructured. This has a significant impact on the large volume of material that cannot be administered in accordance with legal conditions and criteria in Kosovo. The low frequency of cooperation and coordination of activities is negatively affected by the lack of adequate working conditions at the Kosovo State Archives Agency (KSAA), particularly regarding equipment, work tools and, most notably, the insufficient number of staff responsible for exercising KSAA’s legal competencies concerning the archives of record creators and record holders. Evidence of this is the low frequency of inspections, controls and professional field visits.

On the other hand, record creators generally lack the willingness to address the challenges related to the deteriorating condition of the archival material in their possession.

Mostly, the archival material found at the record creators is stored/managed in contradiction with the international practices, norms and standards, which can be considered as at least in a process of gradual degradation. Additionally, it is not properly organized by the professional staff of the record creators’ archives, who have this obligation clearly defined under Law No. 08/L–111 on Archives.

The general description of the condition of the archives and other functions at KSAA:

The archival material managed by the Kosovo State Archives Agency, specifically the central archive and 7 inter-municipal archives, is estimated to be around 9,000 linear meters or approximately 95 million documents, within a physical storage space of approximately 3,043 m². Of this, 2,203 square meters belong to KSAA (specifically, the Central Repository at KSAA with 1,666 m², the Inter-Municipal Archive of Prishtina with 169 m², the space of the former RTP/RTK archive, 96 m², and the Inter-Municipal Archive of Peja with 272 m²). Based on the minimum standards for the placement/storage of materials, considering that in this type of infrastructure, usability includes the vertical space from the floor to the ceiling, this allows for the placement of archival material amounting to 6,294.2 linear meters. Additionally, 840 m² of space is utilized by municipalities or other public institutions, temporarily used by the inter-municipal archives, and this volume of space can accommodate 2,405.7 linear meters of archival material. Currently, the Kosovo State Archives Agency’s storage facilities, in both categories of space, have the capacity to accommodate archival material from record creators or record holders for only approximately 1,000 linear meters of material.

As specified by international archival standards, in order to prevent gradual degradation or the risk of mass destruction of archival material, which is predominantly in paper format, the storage conditions must include the following:

-        The storage space must not be exposed to natural light;

-        The relative humidity level must be between 55% and 65%;

-        The temperature level must not exceed the range of 14°C to 21°C;

-        The storage facilities must be equipped with modern and functional fire protection systems;

-        The storage facilities must be equipped with modern and functional air conditioning systems.

The current spaces managed by the Kosovo State Archives Agency do not meet the conditions and criteria outlined above. This means that the archival material in the KSAA is, at a minimum, in a state of gradual degradation.

Furthermore, the amount of archival material at acute risk due to water penetration, flooding, or other factors exceeds 400 linear meters.

The oldest archival material, primarily paper-based documents held by KSAA, dates from the years 1608 to 2024. Of the total material held by KSAA, approximately 4,469.10 linear meters are organized, which represents about 47% of the total material in KSAA. The remaining portion, or approximately 53%, is either unorganized or in the process of being organized.

Of the total material, KSAA has currently digitized 2.7 million documents, or over 3% of the total amount. Compared to the highest archival institutions in the region, KSAA is still far from reaching a comparable level of digitized archival material.

The number of employees at KSAA who are directly responsible for the care, organization, processing, digitization and restoration of archival material is 62 employees. Of this number, only 46 employees currently have direct responsibility for organizing the archival material. Based on the individual work standards for organizing, which is 8 linear meters per archivist per calendar year, it implies that the archival material held by KSAA, with the current capacity, cannot be organized for the next 13 years, even if no new documents are accepted into KSAA. With the newly approved organizational structure of KSAA, the number of employees responsible for organization and processing should increase from the current 46 to 67. With this structure, based on the 8 linear meters of archival material organized for one (1), the time required to complete the organization of the currently unorganized material in KSAA is reduced from 13 years to 8.5 years, a goal addressed in this Strategy in terms of achieving the percentage according to the timeline of the Strategy.

The described situation at KSAA regarding its limited capabilities to fulfill legal responsibilities is primarily assessed to have resulted from the following factors:

General condition of archives at the record creators:

Regarding the current state of archival material outside KSAA, the challenge is even greater, with a higher potential for damage to the archival material.

Overall, it is estimated that there are approximately 1,059 record creators in Kosovo, namely institutions and entities identified and within the scope of Law No. 08/L-111 on Archives, which, during the performance of their duties, generate archival material that is sent for archiving to the competent archive after the expiration of the deadline set by law. According to an assessment conducted in 2022, it is considered that in the area, at the record creators, the amount of material that has reached 30 or more years and is ready for submission to the archive is 28,170 linear meters, which means that it constitutes more than two-thirds of the total material held by KSAA.

Assessment of KSAA’s infrastructural capacity to manage the handover of mature material found at record creators:

When considering the ratio of physical space currently possessed by KSAA in relation to the archival material it holds and the mature material ready for submission that exists outside KSAA (9,000 linear meters in KSAA and 28,000 linear meters in the field = 37,000 linear meters), it is clear that KSAA must have a total storage space of 14,000 m² to accommodate and manage such material. However, KSAA currently has a total space of 3,043 m². This indicates that KSAA is currently short by 10,957 m².  In the light of the foregoing, it can be concluded that an area of 11,500 square meters of archival storage is essential to be developed for KSAA’s needs by 2029, in order to be able to fulfill the legal obligation for the acceptance and preservation of matured archival material as per the law, for delivery, respectively for permanent storage.

Specifically, the storage ratio, according to standards, is 1 m² for every 1.75 m², and vertical utilization between the floor and ceiling is calculated by multiplying the m² space by a height of 5 meters. This yields a total capacity of linear meters of archival material that can be stored in the designated space. In this case: 14,000÷1.75=8,000*5=40,000, which is the total amount that could be archived, in line with the evaluations of:

- The current volume archived in KSAA’s storage spaces;

- The mature material ready for submission that exists outside the competent archive;

- Material from organizations/individuals that conducted activities in the 1990s;

- Material that will mature after 1999, specifically by 2029;

The extreme years of the total archival material at record creators range from 1800 to 2024; It is considered that all material, whether mature or not, totaling 92,000 linear meters, is stored in spaces that do not meet the storage standards as outlined earlier. This means that this material is at risk of gradual degradation. There is a significant risk of destruction or acute damage to a large quantity, though this cannot currently be quantified due to the lack of accurate data and unsupported statements from responsible officials at record creators. Overall, it is estimated that only about 20% of the total material is properly arranged according to legal obligations at record creators. The number of employees working at record creators responsible for archival care across the Kosovo archive network is approximately 1,000. The amount of material reported as digitalized by record creators is around 5% of the total material.

Implementing a plan, specifically an effective, large-scale, synchronized system with continuous oversight, involving all officials (approximately 1,000 responsible for archives at record creators/holders) in the archival material arrangement and processing process, would create conditions where a total of over 80,000 linear meters of material could be processed within 10 years. (1,000 x 8 linear meters of material arranged per year = 8,000 x 10 years = 80,000 linear meters).

The failure of record creators to handle archival material according to the rules and legal/professional provisions is primarily conditioned by:

- Lack of planned investments in archives by record creators;

- Lack of projects for the proper accommodation of spaces, arrangement of material or its digitalization;

- Lack of plans and projects by record creators to involve their staff in the process of arranging and processing archives, especially the absence of staff training for arrangement, as well as the lack of definition, planning, oversight, and accountability in the process of arranging and processing archival material according to the prescribed standards.

- The lack of continuous supervision and, consequently, the imposition of penal measures according to Law No. 08/L-111 on Archives or the initiation of cases in criminal proceedings in accordance with the Criminal Code and the Criminal Procedure Code, by the KSAA Inspectorate, for archivists of record creators across Kosovo, and most importantly, for the record creators themselves, who, due to the poor condition of the material, should be subject to the sanctions prescribed by law. All of this is due to the lack of basic working conditions regarding the necessary staff, logistics and tools needed for work.

In general, based on the analysis of experiences with countries in the region such as: Croatia, Albania and Montenegro, their difficulties are, or have been, largely similar or identical to those of the Republic of Kosovo. Changes in political, economic and social systems have created space for archives and archival science to not be treated with the priority they deserve. However, later, there was a need for a more sensitive redefinition of public policy measures, legal changes, and increased investments to preserve and protect the documentary archival memory. As in Croatia, Albania and Montenegro, the issues have been primarily solved with diversified measures. The problem of the lack of conditions or physical space for infrastructure has also been identified in these countries and has been addressed through the planning of significant investments in the renovation of existing spaces, finding alternative spaces for archival material storage, or even constructing new spaces, based on the archival material in possession, that which is matured, and that which is awaiting maturation. The problem of processing and organizing archival material has mainly been solved by first legally regulating the obligation of record creators to take responsibility for processing/organizing their material, then strengthening inspection controls and applying legal measures that have directly impacted the activation of record creators’ resources to meet the set standards for processing/organizing material. In some cases, a method of temporary project development has been applied by contracting external entities, natural or legal persons) that are supervised by the competent archives, for the realization of specific projections for the organization and processing of archival material.  The problem with digitalization has mainly been addressed using two types of measures: 1. Investments in technology for employees responsible for public archival units and 2.  Engagement/contracting of external services for digitalizing materials and digital service programs for access to archives are critical measures to address existing challenges.

In general, the lack of investments, as elaborated above, can be quantified through the following analysis:

-        Allocated funds for archives: Both KSAA and the archives of record creators receive a very low percentage of the total funds allocated for other sectors; -        Funds spent against budget allocations: A total of €2,643,635.64 was spent over four years (2020-2023) for both central and local levels. The percentage of budget expenditure relative to the allocated budget over four years for the two levels is 71.29%. Spending for the central level over four years was €1,815,097.91, while for the local level, it was €828,537.73.

| YEAR | DESCRIPTION | BUDGET | EXPENDITURE |
| --- | --- | --- | --- |
| 2020 | CENTRAL LEVEL | 659,651.00 | 447,958.37 |
|  | LOCAL LEVEL | 269,475.29 | 249,148.33 |
|  | TOTAL FOR 2020 | 929,126.29 | 697,106.70 |
| 2021 | CENTRAL LEVEL | 519,072.39 | 243,784.79 |
|  | LOCAL LEVEL | 22,019.00 | 21,470.00 |
|  | TOTAL FOR 2021 | 541,091.39 | 265,254.79 |
| 2022 | CENTRAL LEVEL | 328,000.00 | 19,937.28 |
|  | LOCAL LEVEL | 180,000.00 | 31,216.00 |
|  | TOTAL FOR 2022 | 508,000.00 | 51,153.28 |
| 2023 | CENTRAL LEVEL | 1,139,863.33 | 1,103,417.47 |
|  | LOCAL LEVEL | 590,000.00 | 526,703.40 |
|  | TOTAL FOR 2023 | 1,729,863.33 | 1,630,120.87 |
| 2020-2023 | CENTRAL LEVEL | 2,646,586.72 | 1,815,097.91 |
|  | LOCAL LEVEL | 1,061,494.29 | 828,537.73 |
|  | TOTAL FOR BOTH LEVELS FOR FOUR YEARS | 3,708,081.01 | 2,643,635.64 |

-        There has been no archival institution or repository for archival material built in post-war Kosovo from the beginning, despite the fact that there is a significant lack of space and, consequently, strained conditions for the storage and protection of archival material.

In the current situation, the lack of infrastructural, technical, logistical and technological conditions and especially the necessary human resources for the entire archival network, are among the main causes of the deteriorated condition of the archival material. All of these causes can easily be addressed through government measures, particularly with a medium- and long-term planning structure for budgetary measures. The alternative of budgeting the requests and needs of archives by the government is considered to be the approach of accessing donor funds.

The legal infrastructure, starting with the legislation with horizontal scope, sectoral legislation and criminal legislation, generally provides for good regulation and compliance with international standards, allowing for the planning and direction of resources to target areas with a high potential for negative impact in the area of archives. It is also assessed that the political environment is not expected to produce identifiable negative impacts. Moreover, the economic environment allows space for intervention with the necessary investment measures to achieve the objectives in the area of archives in Kosovo.

Problems that cannot be directly influenced by government measures are primarily related to parts or the entirety of archival material that (i) are in the possession of still unidentified private individuals, or (ii) were taken by force and in violation of the legal provisions of the time of those records or parts of those records by the state of Serbia.

SWOT ANALYSIS

STRENGTHS

- Suitable physical infrastructure space for the central archive of KSAA;

- Professional experience of the current staff of KSAA;

- Harmonized legal framework for the operationalizing and conducting archival activities in the country;

- The newly approved organizational structure through the Regulation (OPM) No. 16/2024 for Internal Organization and Systematization of jobs in KSAA;

- KSAA’s membership in the International Council on Archives;

- Development of capacities for publications and exhibitions both domestically and internationally;

- Development of the project and successful initiation of mass digitalization of archival material;

- Initiation of investments in archival infrastructure.

WEAKNESSES

- Insufficient professional/supporting human resources in the competent archives;

- Insufficient and non-standard physical infrastructure for the preservation of archival materials;

- Insufficient logistical support for normal operation and in accordance with the needs of the competent archives;

- Insufficient public investments in physical, technological/digital infrastructure and human resources in the archival network;

- High percentage of unorganized archival material as a result of the failure to involve the staff in the adequate process of preservation, organization, processing and digitalization of archival materials in the archives of the record creators and special archives;

- Lack of records at the file level for archival material in the archival network;

- Lack of complete records of record creators and record holders, including data on archival materials of value found thereof;

- Small number of inspections/measures taken;

- Small number of convicting judgments from the courts for criminal offenses against archival material.

OPPORTUNITIES

- Development of projects for the expansion and improvement of archival infrastructure, development of projects in Gjilan, Mitrovica, etc.;

- - Possession of a significant amount of archival material created from the end of World War II until the mid-1990s;

- - Development of new professional capacities by utilizing/transferring existing experience;

- Further strengthening of the mass digitalization of archival materials through the financing of the existing project and new investments in digitalizing audio and video materials;

- Facilitation of services for parties through the Post Office;

- Inclusion of archival staff at the record creators;

- Strengthening the supervision of the implementation of work standards related to the organization and processing of archival materials;

- Strengthening scientific and journalistic activities through the use of archival materials;

- Continuous enrichment of the archive through the exchange or research of materials with other archives.

RISKS

- Continuous increase of archival material at risk of destruction/degradation/loss found in competent archives or with record holders due to stagnation in the development of infrastructure, structural organization, and other conditions in the archives;

- Relatively suitable security conditions leading to the loss, destruction, falsification or manipulation of archival materials for the purpose of illegal gain;

- Loss, concealment of archival materials and manipulation of historical facts regarding the 1990s period as a result of the inability to collect and archive materials created by social and political activities of the respective period;

- Lack of budgetary support for the implementation of capital projects;

- Interruption of the digitalization process of archival materials;

- Lack of budgetary support for strengthening the sufficient human resources of KSAA and competent archives;

- Natural disasters.

- VISION AND STRATEGIC OBJECTIVES

The vision of the Strategy is the consolidation and development of a competent, professional archival service capable of ensuring the secure preservation of the country’s archival materials.

To practically implement this vision and address the problems and challenges identified in Chapter 4 of this Strategy, five (5) strategic objectives have been developed with their specific objectives, within which concrete activities will be planned to achieve them.

| Strategic Objective: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objective 1: | Objective 2: | Objective 3: | Objective 4: | Objective 5: |
| Handover and preservation of matured archival material in the competent archive, according to international conditions and standards | Strengthening the processes of processing and regulation of archival material | Digitalization of archival material and increase of digital archival services for parties | Enhancing the research, promotion, cooperation, publishing and scientific research component through archives | Consolidating the implementation capacities of the Kosovo State Archives Agency; |
| Specific Objectives: |  |  |  |  |
| 1 – Full renovation of existing spaces owned or leased long-term by KSAA, in accordance with international archival standards for archival storage facilities. | 1 – Construction/provision of archival storage spaces that meet international archival standards for KSAA’s archival units, including 11,500 square meters of space by 2029. | 1 – Development of professionally trained structures for the management of storage units in competent archives. |  |  |
| 2 – Completion of professional and administrative capacities for the units responsible for the organization and processing of archival material in competent archives. | 2 – Completion of professional and administrative capacities for the units responsible for the organization and processing of archival material in KSAA. | 2 – Development and expansion of the electronic monitoring system in the archival network for the process of organizing and processing archival material by KSAA. | 2 – Development of methodological guidelines/standardization of the methodology for organizing and processing archival material in the archival network, in accordance with international standards. | 2 – Implementation of preventive and/or punitive measures for failure to meet the annual norms for organizing and processing archival material by record creators. |
| 3 – Sustainable funding for the digitalization of paper archival material, with at least 4.5 million documents digitalized in one (1) year at KSAA. | 3 – Development of sufficient and appropriate digital infrastructure for the secure and long-term preservation/management of digital registers. | 3 – Sustainable funding for the digitalization of audio and video archival material. | 3 – Development of a system for the utilization/usage of archival material in digital document form, as well as audio and video content. |  |
| 4 – Continuous enrichment of KSAA with archival materials that are important for the history, culture, and heritage of our country. (Enrichment through research and exchange of materials with regional archives or through acquisition/purchase from private owners) | 4 – Creation/empowerment/operationalization of an online research system for archival material. | 4 – Development of the information platform package for research, through the entry of data into the electronic catalogue with descriptions of archival materials down to the file level, and publishing guides for archival records. | 4 – Promotion of archival wealth through publications, exhibitions, open archive week, conferences, etc. | 4 – Further development of the regional and international cooperation framework with countries’ archives with which we have not yet established agreements. |
| 5 – Increase in KSAA’s budget for technical, logistical and technological support. | 5 – Strengthening KSAA’s inspection capacity for a frequency of 27 inspections per week, 108 inspections per month and 1,296 inspections per year. | 5 – Transfer of municipal archives to the organizational structure of IMA. | 5 – Completion of professional and support organizational structures according to the newly approved structure within three (3) years. |  |

In relation to Objective 1, the Strategy defines a clearly identified set of steps that consist of enhancing and strengthening the infrastructural, technical, logistical, and especially the necessary human and professional capacities of competent archives to enable them to: (i) accept the amount of archival material older than 30 years – matured archival material, (ii) eliminate the risk of acute, irreversible damage or loss, (iii) create appropriate conditions in accordance with internationally defined parameters for the storage of archival material, ensuring it is not exposed to the risk of destruction or acute damage, while simultaneously protecting it from continuous and gradual degradation. The increase in capabilities and capacities for the adequate reception and storage of material in this regard also refers to the central archive and intermunicipal archives of the Kosovo State Archives Agency (KSAA), as the archival units with the greatest responsibilities in the entire archival network, special archives and archives of the record creators, as defined by Law No. 08/L-111 on Archives.

The creation of these conditions to achieve Objective 1 primarily refers to the investments specified in the Action Plan to renovate and bring the physical infrastructure currently possessed/used by KSAA into compliance with international standards, followed by further investments that involve the development of new spaces for the missing portion of infrastructure, estimated/quantified based on the amount of material that has not yet been submitted, even though it has reached the age of 30 years.

Investments for the renovation or development of archival infrastructure refer to the KSAA archives, as the archives with the greatest responsibilities for the volume of material they are responsible for receiving, as well as the creation of human capacity in the archives of the record creators and special archives to effectively manage legal responsibilities for preservation, protection and management according to archival material standards.

Achieving the objective for the expansion of the existing space volume, which is capable of receiving, storing, protecting and managing at least 40,000 linear meters of archival material (9 km existing in KSAA; 28.5 km of matured material found with the record creators and the approximate additional amount of material covering the 1990s period), can be done through:

- Investments in the construction of new storage facilities;

- Investments in the renovation/revitalization of unused existing public buildings.

The development of an archival network capable of receiving archival material created by public and private activities, but with public and social interest, in addition to infrastructure, also requires trained professional and administrative structures for managing storage in competent archives, which is addressed through the specific objective related to the development of trained functional structures.

Objective 2 refers to the tasks and responsibilities of competent archival units for processing/organizing the archival material in possession, according to contemporary technical and professional standards of archival science. Although we are in a period of mass expansion of archive digitalization towards electronic document and material management, the Republic of Kosovo still has a large amount of archival material in physical form, which, in accordance with the applicable laws and international standards, is obliged to ensure the necessary conditions for permanent preservation and professional management. The processing and organizing of archival material is the responsibility of the archival units of the Kosovo State Archives Agency (KSAA), special archives, the archives of record creators/record holders of archives and private archives. The Strategy envisions specific measures and actions aimed at coordination, cooperation and the promotion of an integrated and coherent plan for involving the human and professional capacities of KSAA’s archives, record creators/record holders of archives and special archives in the processing and organizing of material that has not yet been handled, mainly through increasing the staff numbers when a shortage is identified in relation to approved standards, training of current staff, and strengthening the control component and actions concerning the organization and processing of archival material at each competent archive. This will then enable the integration of human, technical, and logistical capacities across all archives in the process of organizing and processing archival material. A specific plan to ensure the full inclusion of employees in archival units in the process of organizing and processing, as a legal obligation, requires investments in KSAA’s electronic systems that enable efficient supervision, as well as effective inspection measures that ensure results in enforcing legality on the ground and consequently achieving the objective of increasing the amount of organized/processed archival material.

Regarding Objective 3, the digitalization of archival material and services, the Strategy envisions achieving several key objectives: (i) ensuring double preservation of materials, both in physical and digitalized form, as a means of guaranteeing the longevity of material in paper, audio or video format, (ii) ensuring the integrity and security of archival material during use, (iii) facilitating, encouraging, and empowering the use of materials by researchers and other parties, and (iiii) further strengthening cooperation with regional and broader archives, etc. The digitalization process in this case will also serve to enhance the efficiency and effectiveness of professional service work in the competent archives.

Within the Objective 4, the goal is to continuously strengthen the capacity of competent archives to publish independently or participate in research and scientific projects, as well as to exchange materials with other countries that are significant to our history, culture and state. The materials held by our archives or those found in the archives of regional and other countries contain highly important documented information that has yet to be made known to the public, the scientific, cultural and professional community in the Republic of Kosovo for study needs and various research projects.

Objective 5 relates to strengthening the administrative, professional and legal control measures of the Kosovo State Archives Agency (KSAA), which is responsible for organizing, managing and overseeing archival activities in the Republic of Kosovo. As the highest archival institution in the Republic of Kosovo, KSAA holds defined responsibilities not only for the volume of material it possesses or is obliged to accept but also for overseeing the implementation of measures in the field among record creators, as well as monitoring the enforcement of standards, criteria, and professional and legal conditions in special and private archives. The achievement of this objective is contingent upon the adoption of concrete measures to enhance the operational and enforcement capacities of this Agency.

- IMPLEMENTATION, MONITORING AND REPORTING ARRANGEMENTS

The implementation of the Strategy aims to achieve strategic and specific objectives, as well as particular activities reflected in the Action Plan and interconnected within a logical framework.

Continuous monitoring and evaluation of the results in implementing objectives and activities will be an integral part of the Strategy process, serving as a key element in its fulfillment.

The Strategy Action Plan defines institutional responsibilities for implementing activities in pursuit of strategic and specific objectives. These institutions are required to report periodically on the level of implementation of activities.

The Minister of Culture, Youth and Sports will play a key role in coordinating the Coordination Group for Monitoring the Implementation of the State Archives Strategy (CGMISAS), while the Kosovo State Archives Agency (KSAA) will serve as the institution responsible for carrying out tasks related to collecting, processing and distributing information regarding monitoring and reporting processes. Additionally, KSAA will be responsible for drafting recommendations and assessments by utilizing the collected data and processing statistics to facilitate the decision-making process of the Coordinating Group for Monitoring the Implementation of the Strategy. KSAA will also provide the necessary technical, logistical, administrative and professional support to CGMISAS in its capacity as the Permanent Secretariat, ensuring the smooth operation and effective decision-making of this mechanism.

Composition of the Coordination Group for Monitoring the Implementation of the State Archives Strategy (CGMISAS):

- Office for Strategic Planning within the Office of the Prime Minister;

- Ministry of Culture, Youth and Sports;

- Ministry of Education, Science and Technology;

- Ministry of Internal Affairs;

- Ministry of Local Government Administration;

- Kosovo State Archives Agency (KSAA);

- The representative of the municipalities, delegated through the representative mechanisms of the municipalities;

- Ministry of Finance, Labour and Transfers;

The Coordination Group for Monitoring the Implementation of the State Archives Strategy (CGMISAS) holds meetings at least once (1) every three (3) months and reviews continuously and systematically collected data, specifically the progress reports prepared by KSAA on the level of implementation of activities outlined in the Action Plan.

The issuance of two regular reports is planned:

- The Semi-Annual Report on the implementation of the Strategy Action Plan, which will present the achievements and challenges in implementing the planned activities; and

- The Annual Report on the implementation of the Strategy, which, in addition to the data from the Semi-Annual Report, will also present the level of objective achievement through specific indicators, incurred budgetary expenditures, and other information in accordance with the Manual on Monitoring Strategic Documents.

The Action Plan will be reviewed every two years by the  Coordination Group for Monitoring the Implementation of the State Archives Strategy (CGMISAS). In case of a need for amendments or modifications, the Minister of Culture, Youth and Sports will submit the revised draft for approval at the meeting of the Government of the Republic of Kosovo.

A comprehensive mid-term review of the Strategy will be conducted in 2027.

The final review will take place in 2032 to assess the overall level of implementation of activities and the achievement of the set objectives.

# BUDGETARY IMPACT AND IMPLEMENTATION OF THE STRATEGY:

The following tables provide a summary of the budgetary impact for implementing the activities outlined in the Action Plan of the SAA. The specific costs of each activity, on the other hand, are presented in the Action Plan.

# BUDGETARY IMPACT AND IMPLEMENTATION OF THE STRATEGY

The following tables summarize the budgetary impact for the implementation of the activities defined in the Action Plan of this Strategy. The specific costs of each activity, on the other hand, are presented in the Action Plan.

|  |  | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- | --- |
| Wages and Salaries |  |  |  |  |
| Goods and Services |  |  |  |  |
| Utilities |  |  |  |  |
| Subsidies and Transfers |  |  |  |  |
| Capital |  |  |  |  |
| Total |  |  |  |  |

Table 1 - Total cost of the Strategy

| Additional Budget from the Upcoming MTBF | Year 0 | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- | --- |
| Number of staff |  |  |  |  |
| Wages and salaries |  |  |  |  |
| Goods and Services |  |  |  |  |
| Utilities |  |  |  |  |
| Subsidies and Transfers |  |  |  |  |
| Capital Expenditures |  |  |  |  |
| Development Partners (donors) |  |  |  |  |
| Existing MTBF |  |  |  |  |
| Wages and salaries |  |  |  |  |
| Goods and Services |  |  |  |  |
| Utilities |  |  |  |  |
| Subsidies and Transfers |  |  |  |  |
| Capital Expenditures |  |  |  |  |
| Financing from Borrowing |  |  |  |  |
| Other (e.g. PPP) |  |  |  |  |
| Total |  |  |  |  |

Table 2 - Proposed sources of funding

Draft Action Plan (2025-2027)

| I. | Strategic Objective 1: Handover and preservation of matured archival material in the competent archive, according to international conditions and standards |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| I.1 | Strategic Goal 1: Full renovation of existing spaces owned or leased long-term by KSAA, in accordance with international archival standards for archival storage facilities |  |  |  |  |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Renovation (including supply, installation and activation of fire extinguishing automated systems, air conditioning and humidity level measurement equipment) - transformation of the existing infrastructure of KSAA into infrastructure that meets international standards for proper archival material storage | Situation in 2025 | Start and completion of renovation - conversion of 400 m² of storage space to meet standards and beginning of renovation of 1,850 m² | Completion of renovation - conversion of 1,850 m² into storage space to meet standards and beginning of renovation of 793 m² | Completion of renovation - conversion of 793 m² into storage space to meet standards |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 1.1.1 | Planning and implementation of the budget for the renovation of existing storage spaces - transformation of the existing infrastructure of KSAA into infrastructure that meets international standards for proper archival material storage | Inclusion of the budget in planning acts/instruments (Year 1: start and completion of renovation of ANK facilities in Peja and Prizren, and start of work on the renovation of the Central Depot; Year 2: completion of renovation of the Central Depot and start of renovation of depots in IMAs in Prishtina, Ferizaj and Gjakova; Year 3: completion of renovations started in Year 2); Issuance of the decision to form the working group for the development of the design task for the renovation of KSAA’s existing spaces; Preparation/announcement of procurement procedures for the development of renovation projects; Announcement of the procedure for the execution of works according to the renovation project; Execution phase of renovation works; Technical acceptance of completed works. | 300,000 | 700,000 | 170,000 | Kosovo Budget | KSAA | MCYS | Existing infrastructure of KSAA, renovated in accordance with international standards for archival storage | 400 m² renovated and 1,850 m² started/archiving in acceptable conditions of an archival material quantity of 1,142 linear meters of archival material | 1,850 m² renovated and 793 m² started/archiving in acceptable conditions of an archival material quantity of 5,285 linear meters of archival material | 793 m² renovated/archiving in acceptable conditions of an archival material quantity of 2,265 linear meters of archival material. |
|  | Total budget for Specific Objective 1: | 1,170,000.00 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: | Kosovo Budget |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Capital Investments |  |  |  |  |  |  |  |  |  |  |

| I.2 | Strategic Goal 2: Construction/provision of archival storage spaces that meet international archival standards for KSAA’s archival units, including 11,500 square meters of space by 2027 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Archival storage space of KSAA provided, with standards and functional | Situation in 2025 | Start of construction of 6,433 m² of archival material storage according to standards: IMAs in Gjilan (2,133 m²), Mitrovica (2,050 m²) and Prizren (2,250 m²): | Continuation of project implementation from the previous year and start of construction of 5,500 m² of KSAA archival space, including construction of IMA in Ferizaj (2,000 m²), annex of IMA in Peja Depository (1,500 m²), annex I of the Central Depository (500 m²), annex II of the Central Depository and IMA in Prishtina (1,000 m²). | Complete completion of projects started in 2025 and continuation/completion of no less than 70% of works started in 2026. |

| No. | Measure | Action | Budget |  |  | Leading institution(s) | Source of funding | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2026 | 2026 | 2027 |
| 1.2.1 | Medium-term planning and start of implementation of projects for the first phase of construction of 6,433 m² of archival material storage, respectively in Gjilan, Mitrovica and Prizren | Inclusion in the planning instruments of the budget (MTBF) Establishment of the Working Group for the development of the design task (Prizren and Mitrovica); Announcement of procurement procedure/contracting of the conceptual and detailed design project for the construction of repository in Prizren; Announcement of the procedure for the execution of works according to the project in Gjilan, Mitrovica and the construction of repositories in Prizren. | 800,000 (budgeted for the construction of IMA – Gjilan with 400,000 Euro, construction of IMA – Mitrovica with 250,000 Euro and development of the project for the construction of storage in IMA – Prizren with 150,000 Euro) | 1,400,000 (budgeted for the continuation of construction of IMA – Gjilan with 700,000 Euro, continuation of construction of IMA – Mitrovica with 500,000 Euro; Continuation of construction of repositories in Prizren with 200,000 Euro; | 1,700,000 (Budgeted for the continuation/completion of construction of IMA – Gjilan with 500,000 Euro; continuation/completion of construction of IMA – Mitrovica with 550,000 Euro; continuation/completion of construction of repositories in Prizren with 650,000 Euro). | Kosovo Budget | KSAA | MCYS | Construction/operationalization of storage spaces for Gjilan, Mitrovica and Prizren |  |  | Permanent storage of 8,692 linear meters of archival material under physical and atmospheric conditions according to standards |
| 1.2.2 | Medium-term/long-term planning and start of implementation of projects for the second phase of construction of 5,000 m² of Annex I and Annex II of the Central Repository, the Annex of IMA in Peja and the construction of IMR in Ferizaj. | Inclusion in the planning instruments of the budget (MTBF); Addressing requests to the respective municipalities for the allocation/designation of locations for the construction of IMA – Ferizaj, the Annex of IMA – Peja and obtaining construction conditions for the construction of Annex I in Prishtina, as well as the designation of the location for the construction of Annex II in Prishtina; Establishment of the Working Group for the development of the design task for the respective projects; Announcement of the procurement procedure for the development of conceptual and detailed design projects for each of the projects; Announcement of the procedure for the execution of works according to the respective projects. | 420.000 (budgeted: development of the project for the construction of IMA – Ferizaj with 150,000 Euro; Development of the project for the construction of the Annex of the IMA – Peja repository with 100,000 Euro; Development of the project for the construction of Annex I of the Central Repository with 70,000 Euro; Development of the project for the construction of Annex II of the Central Repository in Prishtina with 100,000 Euro | 1,200,000 (Budgeted: 400,000 Euro for the construction of IMA – Ferizaj; construction of the Annex of IMA – Peja with 300,000 Euro. Construction of Annex I of the Central Repository with 200,000 Euro; Construction of Annex II of the Central Repository with 300,000 Euro. | 1,300,000 (budgeted for the continuation of construction of IMA – Ferizaj with 450,000 Euro; continuation of construction of the Annex of IMA – Peja repository with 400,000 Euro; continuation of construction of Annex I of the Central Repository with 100,000 Euro; Continuation of construction of Annex II of the Central Repository with 350,000 Euro). | Kosovo Budget | KSAA | MCYS | The second phase of development and capacity building of the infrastructure completed to 70%. |  |  |  |
|  | Total budget for Specific Objective 2: | 6.820,000 Euro |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: | Kosovo Budget |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Capital Investments |  |  |  |  |  |  |  |  |  |  |

| I.3 | Strategic Goal 3: Development of professionally trained structures for the management of storage units in competent archives. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Operationalization/training of the professional and administrative capacities of the competent archives; | Situation in 2025 | Training of 25% of the staff engaged in functional tasks in the archive management units related to the storage of archival material; | Training of 25% of the staff engaged in functional tasks in the archive management units related to the storage of archival material; | Training of 25% of the staff engaged in functional tasks in the archive management units related to the storage of archival material; |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 1.3.1 | Data registration, development of the plan and implementation of mandatory professional training for the management of storage facilities by KSAA and KIPA for the staff of competent archives; | Inclusion in the work plan for organizing trainings according to the applicable normative acts; Implementation of the training plan in cooperation with KIPA; Organization of professional examinations; Inspection control of competent archives to ensure compliance with the conditions, criteria and standards of the physical and technological infrastructure of the storage facilities, and to verify if storage management is carried out by professionally trained staff according to the applicable Regulation on Training; Issuance/implementation of measures by the KSAA Inspectorate in cases of failure to comply with the obligations set by the applicable legal acts by the competent archives; | 0 | 0 | 0 | Kosovo Budget | KSAA/KIPA | MCYS | Number of data registrations for the staff engaged in the management of storage facilities in the competent archives; Number of trained staff in the competent archives; Number of inspection controls for monitoring the functioning of storage facilities in the competent archives by the Agency Inspectorate; Number of measures imposed by the Agency Inspectorate; | Registration, training and/or inspection supervision of 25% of the archival units in the competent archives; | Registration, training and/or inspection supervision of 25% of the archival units in the competent archives; | Registration, training and/or inspection supervision of 25% of the archival units in the competent archives; |
|  | Total budget for Specific Objective 3: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: | Kosovo Budget |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Wages and salaries |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: |  |  |  |  |  |  |  |  |  |  |  |

| 2. | Strategic Objective 2: Strengthening the processes of processing and regulation of archival material |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Strategic Goal 1: Completion of professional and administrative capacities for the units responsible for the organization and processing of archival material in competent archives. |  |  |  |  |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Increase of over 50% in the archival units of competent archives that have the corresponding organizational units filled with the necessary number of professional staff for the organization and processing of archival materials, reaching the individual work norms of organizing 8 linear meters per year for each official. | Situation in 2025 | Development by KSAA of a registry with the data of professional officials engaged in the competent archives in the processes of organizing and processing archival materials – 100% | Organization of training by KSAA and KIPA, based on the methodological guidance in accordance with international standards, related to the processes of organizing and processing archival materials for at least 30% of the competent archives; | Organization of training by KSAA and KIPA, based on the methodological guidance in accordance with international standards, related to the processes of organizing and processing archival materials for at least 40% of the competent archives, as well as the start of the application of punitive measures for non-fulfillment of legal obligations for: - Filling the necessary staff; - Training of staff; Achieving individual annual work norms; |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2026 | 2027 | 2028 |
| 2.1.1 | Inclusion in work plans and implementation of tasks by KSAA regarding the development of a registry for professional officials engaged in the processes of organizing and processing archival materials, organizing training with KIPA and implementing control/inspection supervision measures; | Development of records for the competent archive units regarding the data on materials and staff; Organization of training sessions with KIPA according to a pre-harmonized training calendar; Organization of professional examinations Strengthening controls by KSAA for competent archives; | N/A | N/A | N/A | KB | KSAA | KIPA/MCYS | % of archival units identified, officials engaged, officials trained and measures applied; | 100% of registered archival units and engaged officials; | 30% of competent archive staff engaged in the processes of organizing and processing archival material, trained; | 40% of the competent archive staff engaged in the processes of organizing and processing archival materials, trained along with the percentage of archival units inspected/controlled and the percentage of measures applied; |
|  | Total budget for Specific Objective 1: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Wages and Salaries |  |  |  |  |  |  |  |  |  |  |

| 2.2 | Strategic Goal 2: Completion of professional and administrative capacities for the units responsible for the organization and processing of archival material in KSAA. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | The organizational units in the Central Archive and across the IMAs are staffed with the required number of professional personnel, as determined by Regulation No. 16/2024 on Internal Organization and Systematization of Jobs in KSAA; | Situation in 2025 | 6 | 5 | 5 |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 2.2.1 | Budget planning/allocation for enhancing professional capacities in KSAA’s archival material arrangement and processing units | Inclusion of budget allocations in budget planning instruments; Professional staff training; | 45,144 | 37,620 | 37,620 | Kosovo Budget | KSAA | MCYS | Number of units completed with professional staff | Processing/arrangement of an additional 48 linear meters of archival material in KSAA | Processing/arrangement of an additional 40 linear meters of archival material in KSAA | Processing/arrangement of an additional 40 linear meters of archival material in KSAA |
|  | Total budget for Specific Objective 2: | 120,384 Euro |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Wages and salaries |  |  |  |  |  |  |  |  |  |  |

| 2.3 | Strategic Goal 3: Development and expansion of the electronic monitoring system in the archival network for the process of organizing and processing archival material by KSAA; |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2025 | 2026 | 2027 |
| 1. | The electronic monitoring system for the arrangement and processing of archival material across the entire archival network is functional | 0 | Partially developed | Registration of record creators, record lists, data on the level of arrangement and processing for each record creator/competent archive, as well as the number and details of staff engaged in the electronic monitoring system | Full operationalization of the monitoring system |
| 2. | Increase in the percentage of arranged/processed archival material at record creators/recorder holders | 0 | 0 | 0 | 6,000 linear meters of archival material arranged/processed by the record creator/ record holder |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2026 | 2027 | 2028 |
| 2.3.1 | Budget planning for the development and expansion of the electronic monitoring system for the arrangement and processing of archival material held by record creators/record holders | Inclusion of the project in budget planning instruments Development of terms of reference for the project Procurement procedures for acquiring/developing the electronic system Data inclusion/registration in the system System operationalization | 150,000 | 150,000 | 20,000 | Kosovo budget/ donors | KSAA | IPA | Increase in the percentage of archival material arranged/processed at record creators/holders/competent archives due to enhanced effective supervision and aligned with engaged/employed capacities | 100% of record creators’ archives registered in the system | Inclusion of at least 200 officials/archivists in the monitoring system and the arrangement of at least 1,500 linear meters of material in competent archives | Inclusion of at least 600 officials/archivists in the monitoring system and the arrangement of 4,800 linear meters of material in competent archives |
|  | Total budget for Specific Objective 3: | 320,000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: |  |  |  |  |  |  |  |  |  |  |  |

| 2.4 | Strategic Goal 4: Development of methodological guidelines/standardization of the methodology for organizing and processing archival material in the archival network, in accordance with international standards |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Methodological Guide for the standards of archival material arrangement and processing, aligned with international standards, drafted/approved/published/ distributed | Situation in 2025 | 20% of the staff of record creators/record holders equipped and trained in applying the methodological guideline according to international standards during the arrangement and processing of archival material | 20% of the staff of record creators/record holders equipped and trained in applying the methodological guideline according to international standards | 20% of the staff of record creators/record holders equipped and trained in applying the methodological guideline according to international standards |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 2.4.1 | Planning the drafting and approval process for the methodological guideline on the arrangement and processing of archival material according to standards | - Establishment of the Working Group for drafting/developing the methodological guideline; - Consultation of the draft with stakeholders from responsible archival management institutions; - Approval of the methodological guideline; - Publication of the methodological guideline; - Distribution to record creators/record holders | 2,000 | 0 | 0 | Kosovo Budget | KSAA | MCYS | The number of officials from the record creators who are trained and apply the methodological guideline, and the amount of archival material that is arranged and processed according to these guidelines | 70% of the officials engaged in the competent archives are equipped with physical or electronic copies of the methodological guideline | 30% of the officials engaged in the competent archives are equipped with physical or electronic copies of the methodological guideline | Ensuring the implementation of the methodological guideline in the competent archives for at least 50% of the arranged or more specifically, the controlled/monitored material. |
|  | Total budget for Specific Objective 4: | 2,000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Goods and Services |  |  |  |  |  |  |  |  |  |  |

| 2.5 | Strategic Goal 5: Implementation of preventive and/or punitive measures for failure to meet the annual norms for organizing and processing archival material by record creators |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | The number of measures imposed by the inspection control from KSAA for the record creators/record holders for failing to meet the mandatory work standards in the arrangement and processing of archival material | Situation in 2025 | No less than 20 measures imposed | No less than 100 measures imposed | Imposition of measures for each record creator included in the electronic monitoring system who does not meet the annual rate according to the number of staff in the ratio: 1 official = 8 linear meters of material arranged |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 2.5.1 | Staff and other resource planning and implementation of the inspection plan with a focus on the arrangement and processing of archival material by the record creator/record holder | - Physical and/or electronic monitoring of the achievement of individual work rates; - Execution of the planned and focused inspection on arrangement/processing; - Re-inspections; - Imposition of measures proportional to the identified violation and the damage caused | N/A | N/A | N/A | Budget of the Republic of Kosovo | KSAA | N/A | Raising awareness through an increase in the percentage of the implementation of the overall plan for the arrangement of archival material across the entire archival network; | An increase of 20% in the amount of archival material arranged by record creators and record holders compared to the previous year; | An increase of 30% in the amount of archival material arranged by record creators and record holders compared to the previous year; | An increase of 30% for material arranged by record creators and record holders. |
|  | Total budget for Specific Objective 5: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: |  |  |  |  |  |  |  |  |  |  |  |

| 3. | Strategic Objective 3: Digitalization of archival material and increase of digital archival services for parties |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Strategic Goal 1: Sustainable funding for the digitalization of paper archival material, with at least 4.5 million documents digitalized in one (1) year |  |  |  |  |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Number of documents digitalized with the current EO and the continuation of the process with the contracting of EO from 2027 | 2.5 million documents digitalized | 4 million documents | 4 million documents | 4 million documents |
| 2. | Number of documents digitalized by KSAA staff | Situation in 2025 | 560.000 million documents digitalized | 560.000 million documents digitalized | 560.000 million documents digitalized |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2026 | 2027 | 2028 |
| 3.1.1 | The continuation of digitalizing archival documents with the current EO as well as the contracting of EO for the continuation of digitalizing archival materials from 2027. | 1. Provision of OE with material for digitization; 2. Quality control of digitalized documents; 3. Monitoring and management of the project; 4. Procurement planning; 5. Initiating and developing the procurement procedure; 6. Evaluation of received bids; 7. Selection and publication of the winning EO; 8. Signing of the contract; | 280.000 | 280.000 | 280,000 | Kosovo Budget | KSAA | MCYS | 1. Increase in the number of digitized documents; 2. Digitalization of archival documents according to applied standards. | 1. Increase in the number of digitalized documents by 4 million, 2. Improvement in service delivery; 3. Protection of archival material in the physical form of documents | 1. Increase in the number of digitalized documents by 4 million, 2. Improvement in service delivery; 3. Protection of archival material in the physical form of documents | 1. Increase in the number of digitalized documents by 4 million, 2. Improvement in service delivery; 3. Protection of archival material in the physical form of documents |
| 3.1.2 | Operationalization of the digitalization process in 7 IMAs | 1. Appointment of officials for digitalization; 2. Training of officials; 3. Preparation of material for digitalization; 2. Quality control of digitalized documents; | N/A | N/A | N/A | Kosovo Budget | KSAA | MCYS | Increase in the number of digitalized documents at 7 IMAs | 1. Increase in the number of digitalized documents by 560.000 documents; 2. Improvement in service delivery; 3. Protection of archival material in the physical form of documents | 1. Increase in the number of digitalized documents by 560.000 documents; 2. Improvement in service delivery; 3. Protection of archival material in the physical form of documents | 1. Increase in the number of digitalized documents by 560.000 documents; 2. Improvement in service delivery; 3. Protection of archival material in the physical form of documents |
|  | Total budget for Specific Objective 1: | 840.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: | 840.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: |  |  |  |  |  |  |  |  |  |  |  |

| 3.2 | Strategic Goal 2: Development of sufficient and appropriate digital infrastructure for the secure and long-term preservation/management of digital registers |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2025 | 2026 | 2027 |
| 1. | Providing the electronic system for the utilization and management of archival documents. | 0 | Testing phase of the electronic system | Completion, utilization/usage and maintenance of the system | Utilization/usage and maintenance of the system |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 3.2.1 | Operationalization of the document management system. | 4. Procurement planning; 2. Initiating and developing the procurement activity; 3. Evaluation of received bids; 4. Selection of the winning operator; 5 Signing the supply and maintenance contract. 6. Long-term system operationalization and maintenance; | 103.000 | 3.000 | 3,000 | Kosovo Budget | KSAA | MCYS | Application of the system, long-term storage and administration, as well as the enhancement of online service delivery. | Increase and improvement of service delivery by 30% | Increase and improvement of service delivery by 30 % | Increase and improvement of service delivery by 40 % |
|  | Total budget for Specific Objective 2: | 109.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: | Capital Investments |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: |  |  |  |  |  |  |  |  |  |  |  |

| 3.3 | Strategic Goal 3: Sustainable funding for the digitalization of audio and video archival material |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2025 | 2026 | 2027 |
| 1. | Percentage of digitalization of audio and video archival materials. | 0 | 10 % | 30% | 30% |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 3.3.1 | Development of procedures and selection of EO for the digitalization project of audio and video archival materials | 1. Procurement planning; 2. Initiating and developing the procurement activity; 3. Evaluation of received bids; 4. Selection of the winning operator; 5 Signing the supply and maintenance contract. 6. Long-term project operationalization and maintenance; | 160.000 | 160.000 | 160.000 | Kosovo budget/donors | KSAA | MCYS | Progressive increase in the percentage of audio and video material digitalized. Progressive increase in the percentage of audio and video material utilized | Digitalization of 10% of audio and video materials | Increase in the number of digitized audio and video materials by 30% | Increase in the number of digitized audio and video materials by 30% |
|  | Total budget for Specific Objective 3: | 480.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: | 480.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: |  |  |  |  |  |  |  |  |  |  |  |

| 3.4 | Strategic Goal 4: Development of a system for the utilization/usage of archival material in digital document form, as well as audio and video content. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2025 | 2026 | 2027 |
| 1. | Percentage of completion of the Broadcast Management System for utilizing digital document materials and audio and video content. | 0 | 0% | 0% | Start of the application of the Broadcast Management System and utilization/operation and maintenance of the system |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 3.4.1 | Operationalization the Broadcast Management System for utilizing digital document materials and audio and video content. | 1. Procurement planning; 2. Initiating and developing the procurement activity; 3. Evaluation of received bids; 4. Selection of the winning operator; 5. Signing of the contract for supply and maintenance for renting the equipment for the Broadcast Management System; 6. Operationalization and maintenance. | N/A | 150.000 | N/A | Kosovo Budget | KSAA | MCYS | Increase in the percentage of digital, audio and visual documents in the system for utilization/usage of archival material. | N/A | Utilization/usage of 10% of digital, audio and video materials | Utilization/usage of 100% of digital, audio and video materials |
|  | Total budget for Specific Objective 4: | 150.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: | 150.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: |  |  |  |  |  |  |  |  |  |  |  |

| 4. | Strategic Objective 4: Enhancing the research, promotion, cooperation, publishing and scientific research component through archives |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Strategic Goal 1: Continuous enrichment of KSAA with archival materials that are important for the history, culture, and heritage of our country. (Enrichment through research and exchange of materials with regional archives or through acquisition/purchase from private owners) |  |  |  |  |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | The number of research conducted using archival materials that is important for the Republic of Kosovo both domestically and internationally by KSAA | Situation in 2025 | 2 researches (2 Regional Archives) | 2 researches (2 Regional Archives) | 2 researches (2 Regional Archives) |
| 2. | Support for research projects for external experts and researchers | 0 | 0 | 5 research projects | 5 research projects |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2026 | 2027 | 2028 |
| 4.1.1 | Budget planning for the research of archival materials that are important for the Republic of Kosovo | Inclusion in the budget planning instruments (MTEF) | 10.000 | 10.000 | 10.000 | Kosovo budget | KSAA | MCYS/MFLT | Number of reports/materials researched that contribute to enriching the archives with researched or exchanged materials from regional archives | Research result report and submission of physical or digital copies of documents | Research result report and submission of physical or digital copies of documents | Research result report and submission of physical or digital copies of documents |
| 4.1.2 | Budget planning for the research of archival materials that are important for the Republic of Kosovo | 1. Inclusion in the budget planning instruments (MTBF) 2. Drafting and publishing the public call with relevant criteria 3. Evaluation of applications 4. Announcement of results 5. Examination of complaints 6. Publication of the final list of beneficiaries 7. Monitoring the project implementation | 0 | 25.000 | 25,000 | Kosovo budget | KSAA | MCYS/MFLT | Enrichment of the research records in KSAA | 0 | Reports on the research results for 5 supported projects | Report on the research results for 5 supported projects |
|  | Total budget for Specific Objective 1: | 80.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Goods and services and subsidies and transfers |  |  |  |  |  |  |  |  |  |  |

| 4.2 | Strategic Goal 2: Creation/empowerment/operationalization of an online research system for archival material |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Development of digital infrastructure – online research program, functional and interconnected with archives in the region and beyond | Situation in 2025 | Start of the implementation of the online research program by parties submitting research requests to KSAA for research | Full operationalization of the online research program and the beginning of networking the KSAA system with regional and broader archives | Networking the KSAA system with regional and broader archives |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 4.2.1 | Project development planning for the online research program; | Budget planning; Development of the terms of reference for the program; Procurement of program development; Program operationalization | N/A accommodated in Strategic Objective 3, Specific Objective 2 | N/A accommodated in Strategic Objective 3, Specific Objective 2 | N/A accommodated in Strategic Objective 3, Specific Objective 2 | Kosovo budget | KSAA | MCYS | Level of administration of research requests through online and onsite programs. | 5% of research requests – piloting the online program | 50% of research requests are made online | 100% of research requests are completed online and at least 3 regional archives are connected to the online research program |
|  | Total budget for Specific Objective 2: | Accommodated in Strategic Objective 3, Specific Objective 2 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: |  |  |  |  |  |  |  |  |  |  |  |

| 4.3 | Strategic Goal 3: Development of the information platform package for research, through the entry of data into the electronic catalogue with descriptions of archival materials down to the file level, and publishing guides for archival records |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Percentage of data entry with descriptions of archival materials up to the file level in the electronic research catalog, a module of the electronic archival material management system | Situation in 2025 | 15 % | 35 % | 50 % |
| 2. | Number of guides published for archival records | Situation in 2025 | 0 | 0 | 1 |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 4.3.1 | Publishing the catalog with descriptions of archival materials up to the file level, according to the International Standard ISAD (G) | - Appointment of responsible officials for project implementation; - Collection of existing data from the information tools of KSAA; - Extraction of data from archival materials; - Inputting them into the system. | - N/A | N/A | N/A |  | KSAA | MCYS | Increase in the percentage of data entry with descriptions of archival materials up to the file level in the electronic research catalog | Entry of 15% of the data with descriptions of archival materials up to the file level in the catalog | Entry of 35 % of the data with descriptions of archival materials up to the file level in the catalog | Entry of 50% of the data with descriptions of archival materials up to the file level in the catalog |
| 4.3.2 | Publication of the archival record Guide. | - Establishment of the Working Group for the preparation of the Guide; - Extraction of data for KSAA’s archival records; - Preparation for publication; - Publication of the Guide. | N/A | N/A | 3000 | Budget of the Republic of Kosovo | KSAA | MCYS | Guide published | 0 | 0 | 1 |
|  | Total budget for Specific Objective 3: | 3000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Goods and services and subsidies |  |  |  |  |  |  |  |  |  |  |

| 4.4 | Strategic Goal 4: Promotion of archival wealth through publications, exhibitions, Open Archive Week, conferences, etc. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Publication of the Magazine “Albanian Archives”", a joint publication with the General Directorate of Archives (GDA); Publishing a thematic magazine; Resumption of publication of the KSAA annual magazine “Yearbook”; | Situation in 2025 | 2 | 3 | 3 |
| 2. | Exhibition with archival materials | Situation in 2025 | 2 | 2 | 2 |
| 3. | Open Archive Week | Situation in 2025 | 1 | 1 | 1 |
| 4. | Nationwide Conference on Archival Studies, co-organized by KSAA and GDA of Albania; | Situation in 2025 | 1 | 1 | 1 |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 4.4.1 | Published: - Magazine “Albanian Archives”, a joint publication with the GDA of Albania; - A thematic journal with a compilation of archival materials; - Journal “Yearbook”; | - Organizing public calls for publications; - Selecting topics and preparing journals for publication; - Publishing and promoting them. | 15,000 | 20,000 | 20,000 | Budget of the Republic of Kosovo | KSAA | MCYS | Three magazines published in the planned years | 2 | 3 | 3 |
| 4.4.2 | Exhibitions with open archival materials. | - Determining the topics for Exhibitions; - Selecting archival materials; - Curating the exhibitions and their opening; | 2000 | 2000 | 2000 | Budget of the Republic of Kosovo | KSAA | MCYS | Three exhibitions opened in the planned years | 2 | 2 | 2 |
| 4.4.3 | Activity: Open Archive Week, organized | - Preparation of the activity program: Open Archive Week; - Publishing the announcement for the organization of the activity; - Organizing the one-week event. | N/A | N/A | N/A | Budget of the Republic of Kosovo | KSAA | MCYS | Open Archive Week activity, organized | 1 | 1 | 1 |
| 4.4.4 | Nationwide Conference on Archival Studies, joint organization with GDA of Albania; | Organizing a public call for paper submissions for the conference; Receiving abstracts; Selecting them; Organizing and holding the conference. | 5000 | 10,000 | 5000 | Budget of the Republic of Kosovo | KSAA | MCYS | Nationwide Conference on Archival Studies, held; | 1 | 1 | 1 |
|  | Total budget for Specific Objective 4: | 81,000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Goods and services and subsidies |  |  |  |  |  |  |  |  |  |  |

| 4.5 | Strategic Goal 5: Further development of the regional and international cooperation framework with countries’ archives with which we have not yet established agreements. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | New agreements signed with archives of states with which we do not yet have agreements | Situation in 2025 | Negotiating and signing agreements with at least two (2) states | Negotiating and signing agreements with at least two (2) states | Negotiating and signing agreements with at least two (2) states |
| 2. | Participation in international events organized by states with which we do not yet have agreements | Situation in 2025 | Participation in at least two (2) international activities/events in the area of archives | Participation in at least two (2) international activities/events in the area of archives | Participation in at least two (2) international activities/events in the area of archives |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 4.5.1 | Development of negotiations and determination of the structure of cooperation with the respective countries; | Planning the budget for hosting foreign delegations or visits abroad; Conducting procedures for obtaining approval through the Ministry of Foreign Affairs and Diaspora of the Republic of Kosovo; | 10,000 | 10,000 | 10,000 | Budget of the Republic of Kosovo | KSAA | MCYS/MFAD | Number of new agreements reached; | 2 | 2 | 2 |
|  | Total budget for Specific Objective 5: | 30,000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | 30,000 |  |  |  |  |  |  |  |  |  |  |

| 5. | Strategic Objective 5: Consolidating the implementation capacities of the Kosovo State Archives Agency |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Strategic Goal 1: Increase in KSAA’s budget for technical, logistical and technological support |  |  |  |  |
| No. | Indicator | Baseline value | 2026 | 2027 | 2028 |
| 1. | Provision of sufficient vehicles for the operational functioning of the organizational units of KSAA. | 1 | 2 | 3 | 2 |
| 2. | Meeting the IT equipment supply requests from KSAA staff. | Situation in 2025 | 25% | 25% | 25% |
| 3. | Meeting the internal inventory requests. |  | 25% | 25% | 25% |
| 4. | Number of supplies for the restoration and conservation of archival materials. |  |  |  |  |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 5.1.1 | Purchase of 7 vehicles to increase the number of inspections | - Procurement planning; - Initiating and developing the procurement activity; - Evaluation of bids; - Selection and publication of the supplier; | 60.000 | 90.000 | 60.000 | Kosovo budget | KSAA | MCYS | Increase in field activities of KSAA staff – enhancing interaction between KSAA and other competent archives. | 50% increase in the number of inspections per year. | 25 % increase in the number of inspections per year. | 25 % increase in the number of inspections per year. |
| 5.1.2 | Supply of 2 servers and other technology equipment for KSAA; | - Procurement planning; - Initiating and developing the procurement activity; - Evaluation of bids; - Selection and publication of the supplier; | 35.000 | 35.000 | 25.000 | Kosovo budget | KSAA | MCYS | Improvement of the digital infrastructure for the storage and protection of digital documents on KSAA’s servers. | 35% increase in temporary storage capacity for digital documents. | 35% increase in temporary storage capacity for digital documents. | 30% increase in capacity for temporary storage of digital documents. |
| 5.1.3 | Fulfilling internal inventory supply requirements. | - Procurement planning; - Initiating and developing the procurement activity; - Evaluation of bids; - Selection and publication of the supplier; | 40.000 | 20.000 | 20.000 | Kosovo budget | KSAA | MCYS | Improving working conditions | Continuous improvement of the quality of professional services. | Continuous improvement of the quality of professional services. | Continuous improvement of the quality of professional services. |
| 5.1.4 | Supplying the relevant unit with equipment for the restoration and conservation of archival material. | - Procurement planning; - Initiating and developing the procurement activity; - Evaluation of bids; - Selection and publication of the supplier; | N/A | 50.000 | 25.000 | Kosovo budget | KSAA | MCYS | Application of work tools in fulfilling work tasks in restoration and conservation | N/A | Providing 70% of the inventory for work in the document restoration and conservation service. | Providing 30 % of the inventory for work in the document restoration and conservation service. |
|  | Total budget for Specific Objective 1: | 460.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: | Capital 380,000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Goods and Services: 80,000 |  |  |  |  |  |  |  |  |  |  |

| 5.2 | Strategic Goal 2: Strengthening KSAA’s inspection capacity for a frequency of 27 inspections per week, 108 inspections per month and 1,296 inspections per year. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2025 | 2026 | 2027 |
| 1. | Number of staff recruited for the inspection unit | 3 | 8 inspectors recruited | N/A | N/A |
| 2. | Number of training courses for inspectors and their certification | 0 | 11 inspectors trained and certified | N/A | N/A |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 5.2.1 | Development of procedures and recruitment of 8 officers in the inspection unit. | - Planning the recruitment procedure; - Announcement of the competition; - Evaluation of applicants; - Announcement of final results. - Signing of the Employment Letter. | 89.000 | 89.000 | 89.000 | Kosovo budget | KSAA | MCYS | Increase in the percentage of inspections at the record creators/ record holders. | 50% | 50% | 100% |
|  | Organization and development of training and certification of inspectors. | - Training planning; - Participation in the training; - Inspection testing; - Certification of inspectors; | N/A | N/A | N/A |  |  |  | Trained and certified inspection unit staff. | 100% | N/A | N/A |
|  | Total budget for Specific Objective 2: | 267.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Wages and salaries |  |  |  |  |  |  |  |  |  |  |

| 5.3 | Strategic Goal 3: Transfer of municipal archives to the organizational structure of IMAs. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2025 | 2026 | 2027 |
| 1. | Number of municipal archives transferred within the organizational structure of the IMAs. | 0 | 3 former municipal archives transferred within the structure of the respective MMA.. | 4 former municipal archives transferred within the structure of the respective MMA.. | 3 former municipal archives transferred within the structure of the respective MMA.. |
| 2. | Percentage of funding for expanded capacities | 0 | 30 % | 40 % | 30 % |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 5.3.1 | Holding meetings to define the steps towards reaching an agreement with 10 municipalities that manage former municipal archives. | - Holding meetings with the municipalities; - Agreeing on the forms of transferring the current staff; - Discussing ways to take possession of the spaces; | N/A | N/A | N/A | Kosovo budget | KSAA/MUNICIPALITIES | MCYS | - Number of meetings held with municipalities; - Number of agreements reached with competent municipalities; - Application and implementation of the agreements reached. | 30 % | 40 % | 30 % |
| 5.3.2 | Analysis/evaluation of the budgetary costs of the Agency due to the expansion of spaces/material/staff from the transfer of former municipal archives to KSAA. | - Consultation with the MFLT; |  |  |  | Kosovo budget | KSAA/MUNICIPALITIES | MFLT | Formalization of the budget support scheme for KSAA against the costs incurred. |  |  |  |
|  | Total budget for Specific Objective 3: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: |  |  |  |  |  |  |  |  |  |  |  |

| 5.4 | Strategic Goal 4: Completion of professional and support organizational structures according to the newly approved structure |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Indicator | Baseline value | 2025 | 2026 | 2027 |
| 1. | Percentage of filling positions provided for in the Regulation on Internal Organization. | 102 | 3 | 5 | 5 |

| No. | Measure | Action | Budget |  |  | Source of funding | Leading institution(s) | Supporting institution(s) | Deliverable |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year N1 | Year N2 | Year N3 |  |  |  | Measure indicators | Values |  |  |
|  |  |  |  |  |  |  |  |  |  | 2025 | 2026 | 2027 |
| 5.4.1 | Filling professional positions to meet the KSAA objectives. | - Planning the recruitment procedure; - Announcement of the competition; - Evaluation of applicants; - Announcement of final results; - Signing of the Employment Letter; | N/A | 182.000 | 182,000 | Kosovo budget | KSAA | MCYS | Number of successful recruitment procedures. | Filling three (3) vacant positions | Filling 5 positions following the recruitment procedures | Filling 5 positions following the recruitment procedures |
|  | Total budget for Specific Objective 4: | 364.000 |  |  |  |  |  |  |  |  |  |  |
|  | Of which capital: |  |  |  |  |  |  |  |  |  |  |  |
|  | Of which current: | Wages and Salaries |  |  |  |  |  |  |  |  |  |  |